## Slide 1
verity
Verity for
D & S Electric Works
What we heard, what we propose, and what it costs.
Proposal meeting · 21 October 2026
Prepared by PlotArmour for D & S Electric Works, Rau, Indore
Enquiry
Quote
Order
BOM
Make
Test
Dispatch
Notes: Opening. Thank the team for the two detailed calls. The deck has three parts: what we understood from you, the three options with prices, and how it runs on your server. Everything here is from the written proposal; nothing is new pricing.

## Slide 2
What we heard from you
Six things you told us over the two calls. These shape the whole proposal.
Numbers you define
Document numbers built from your own positions: country, organisation, division, section, type. Characters 0 to 9 and A to Z.
Traceability to origin
Down to every sub-component of an assembly, with visible revisions (R01, R02) and the drawing actually used.
Checklists you build
Per client and per product, with photo and video approval. No call to us for every new product.
Test reports in ten seconds
Summary first, detail only on a failure. Every value in the right unit, with the condition it was tested under.
One project file at the end
Photos, drawings and records in one stamped document you can submit to the customer.
Your server, your data
NDA-bound client data stays on your own server. Shop-floor staff use Android phones. Staff are not technical.
Also raised: full source code and independence from any vendor · attendance that reaches payroll without re-entry · Hindi and English labels on the shop floor
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
2
Notes: Read these back to the client in his own words and ask: did we miss anything? Source: the call transcripts of 19 October (auto-captioned, noisy), summarised in clients/dsew/decisions.md. These are client-stated, not yet confirmed in writing.

## Slide 3
One job, from enquiry to dispatch
Every order is an engineered job. One record carries it through every step, so nothing is retyped.
1
Enquiry
Customer, contact, requirement
2
Quote
Revisions, approval, lost reason
3
Order
Job, milestones, tasks
4
Engineering
BOM, revisions, drawings
5
Materials
Purchase, receipt, stock
6
Make
Stages, travellers, hold and resume
7
Test
Readings, units, pass or fail
8
Dispatch
Pack, delivery note, QR identity
A failed or missing mandatory check blocks release.
Nothing leaves the factory without its checks, and a released revision cannot be edited. A change creates a new revision through approval.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
3
Notes: This chain is the scope. Steps 1 to 8 appear in both options; the Complete ERP adds depth at each step plus finance, HR and payroll, contracts and AI use cases.

## Slide 4
Your needs, and where each one lands
Covered by the proposal, in the option shown.
NEED
HOW VERITY ANSWERS
IN
Document numbering you define
Configurable numbering per document type; each client counts on its own; search by number
Both options
Which drawing was used
Revision history; the order records its revision; a released revision cannot be edited
Both options
Test report, summary first
Verdict first; each reading in a fixed unit against its accepted range, with its test condition
Both options
Shop floor on Android phones
Responsive screens; camera opens for photo checks; QR scan on the order returns after sign-in
Both options
Traceability to origin
MVP: basic material and job references. Complete: batch, heat and serial tracking, product genealogy
Complete
Payroll without re-entry
Attendance, leave, timesheets and payroll runs on your rules, in one system
Complete
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
4
Notes: 'Both options' means present in Option 1 (MVP) and Option 2/3 (Complete). Depth differs: see the comparison slide. Traceability to every sub-component is a Complete-ERP item and its exact depth is still a decision for DSEW (next slide).

## Slide 5
Five things only you can decide
Each one changes scope or cost. We will not assume an answer.
Traceability depth
Lot or heat on receipt, serial numbers, or every sub-component of every assembly?
Baseline: lot or heat and certificate on receipt, issue to order, unique unit identity. Full genealogy costs more.
Hindi labels
Hindi and English labels for shop-floor staff on Android.
Not in the current scope. We keep text in one place so it stays possible. Tell us if it is a go-live requirement.
Attendance machine
eSSL K90 export into Verity, so no re-entry into payroll.
Payroll is in Complete. Device integration is excluded until we confirm the model and its export or API.
Client accounts
3 to 4 customer users per project who raise tickets and see shared drawings.
Not in the current module list. Needs scope and a price before we promise it.
Checklist builder
Forms you build yourself with photo and video approval fields.
Configurable travellers and checkpoints are in. A builder you operate alone is confirmed in the specification.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
5
Notes: Ask for a decision or a date on each row. Sources: clients/dsew/decisions.md (D2, D7 and the call findings of 19 Oct) and proposal section 9 and document 2 section 9 (Hindi interface labels not included). The customer-portal expectation conflicts with the read-only portal in the PRD.

## Slide 6
What already runs, and what we build for you
We say which is which, so you are never surprised.
Running in Verity today
Per-company data isolation, roles and permissions, audit trail
Stock ledger with reversal-only corrections
Manufacturing orders from a BOM, stages, hold and resume
Quality checkpoints with evidence that block completion
Project jobs: milestones, tasks, time, costs, quote revisions and approval
Printable traveller, dispatch pack, QR identity for a finished unit
Run on our test environments with fictional data.
Built for DSEW in this project
Revision-controlled BOM and engineering change
Controlled documents with your numbering
Structured test records and the printable test report
Procurement, inventory and planning depth, MRP
Traceability, dispatch, contracts, dashboards
Finance, HR and payroll, documented AI use cases (Complete)
Not yet tested on your host. See the go-live gates.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
6
Notes: Source: document 4 section 2 of the proposal. Verity is our own platform; the proposal does not claim past ERP, MES or QMS deployments. Offer the live demo after the pricing section.

## Slide 7
Three ways to buy, one price each
One-time fee, ex GST. No per-user or annual licence. Up to 15 named users, one site.
OPTION 1
MVP
Core engineering and manufacturing ERP: enquiry to quote to order, BOM, materials, manufacturing, travellers, quality.
₹3,25,000
₹3,83,500 incl. 18% GST
Delivery 6 to 8 weeks
First 12 months, ex GST ₹4,27,000
OPTION 2
Complete ERP
All 19 modules of your enquiry plus documented AI use cases, with deeper workflows and cross-module links.
₹4,80,000
₹5,66,400 incl. 18% GST
Delivery 8 to 12 weeks
First 12 months, ex GST ₹5,82,000
OPTION 3
Our suggestion
Complete, in four phases
The same Complete ERP and the same price, delivered in four phases with a demonstration and acceptance at each.
₹4,80,000
₹5,66,400 incl. 18% GST
Delivery 8 to 12 weeks
First 12 months, ex GST ₹5,82,000
First 12 months = one-time fee plus the bundled ₹1,02,000 warranty, testing support and maintenance fee. Timelines are estimates, not fixed deadlines.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
7
Notes: Prices and scope are as agreed in the proposal dated 20 October 2026, valid 60 days. Option 3 is an alternative delivery structure for Option 2, not an additional purchase. IGST expected (our GSTIN is Delhi, DSEW is in Madhya Pradesh); confirmed at invoicing. The 'Our suggestion' label is our view, the client's choice.

## Slide 8
Option 1: MVP, ₹3,25,000
Nine modules plus implementation. One connected workflow from enquiry to delivery readiness.
Chart: 
| CRM, enquiry and quotation | Project and order management | Document management and numbering | Basic engineering and BOM | Basic procurement and inventory | Manufacturing execution and jobs | Manufacturing traveller | Core quality management | Dashboards and basic notifications
Price (₹, ex GST) | 35000 | 25000 | 35000 | 35000 | 40000 | 40000 | 25000 | 30000 | 15000
Where the ₹3,25,000 goes
Module development
2,80,000
Requirements and design
12,000
Configuration and deployment
10,000
Testing and UAT support
12,000
Documentation, training
11,000
Not in the MVP
Finance and accounting, HR and payroll, dispatch workflow, contracts and compliance, advanced MRP, barcode genealogy, AI.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
8
Notes: Source: proposal section 3. Prices in rupees, excluding GST. The MVP is roughly 55% of the Complete ERP's functional scope (a planning estimate) and priced at about 68% of it, because the foundations are needed in both.

## Slide 9
Option 2: Complete ERP, ₹4,80,000
Nineteen modules, built inside Verity. No third-party software to buy.
Chart: 
| CRM, enquiry, quotation, sales order | Advanced project management | Engineering and product lifecycle | Controlled document workflows | Manufacturing execution | Travellers and process documents | Quality management system | Barcode, QR and traceability | Procurement and vendors | Inventory and warehouse | Production planning and basic MRP | Testing and equipment | Finance and accounting | HR and payroll | Dispatch and logistics | Contracts, compliance, risk | Management dashboards and BI | Notifications and automation | AI, documented use cases
Price (₹, ex GST) | 30000 | 20000 | 30000 | 25000 | 30000 | 15000 | 25000 | 15000 | 20000 | 20000 | 20000 | 15000 | 20000 | 15000 | 10000 | 10000 | 15000 | 15000 | 15000
Where the ₹4,80,000 goes
19 modules
3,65,000
Requirements and architecture
25,000
UI/UX and workflow configuration
20,000
Integration and deployment
25,000
Testing and UAT support
20,000
Documentation and training
15,000
Governance
10,000
Agreed baseline depth
Standard workflows and limited customisation, fixed in a written specification before development starts. Outside it: advanced AI, bulk historical migration, statutory certification, third-party integrations.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
9
Notes: Source: proposal section 4. Module development 3,65,000 + implementation 1,05,000 + governance 10,000 = 4,80,000. Price difference to the MVP is 1,55,000 (about 47.7% more).

## Slide 10
MVP versus Complete, where it matters to you
The ₹1,55,000 difference buys breadth and depth. These are the rows that map to what you asked for.
Module | Option 1: MVP | Option 2 / 3: Complete
Engineering and PLM | Product and component records, BOMs, drawing attachments, revisions | Multi-level BOMs, engineering change orders, formal design approvals
Document management | Repository, numbering, revision history, search, basic approvals | Full controlled-document lifecycle, transmittals, acknowledgements, audit
Quality | Incoming, in-process and final inspection, NCRs, quality release | QAP/ITP, CAPA, audits, calibration, supplier quality, analytics
Traceability | Basic material and job references, manual tracking | Barcode scanning, batch, heat and serial, product genealogy
Inventory and planning | Stock balances, issues, reservations; manual material planning | Multi-warehouse, valuation, ageing; automated BOM-based MRP
Finance and accounting | None | Invoicing, payment status, GST support, receivables and payables, profitability
HR and payroll | None | Attendance, leave, payroll runs on your rules, payslips
AI | Not included | Documented use cases only; never an approver
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
10
Notes: Full 19-row comparison is in proposal section 5 and the Scope Comparison sheet. Choose rows that match his priorities: traceability, documents, test records, payroll.

## Slide 11
Option 3: the Complete ERP in four phases
Same ₹4,80,000, about 8 to 12 weeks. Each phase ends in a demonstration and a written review.
1
Weeks 1 to 3
Foundation and commercial core
Linked customer, enquiry, quotation, order and project, with controlled numbering, initial engineering masters and BOM.
₹1,20,000
2
Weeks 3 to 6
Supply chain and manufacturing
A BOM drives material needs for a job; purchases, receipts and stock recorded; engineering release works. First backup and restore rehearsal.
₹1,35,000
3
Weeks 5 to 9
Quality, traceability, controls
Travellers and inspections linked; traceability, testing, dispatch, contracts work; a failed mandatory check blocks release.
₹1,30,000
4
Weeks 7 to 12
Business modules and go-live
Finance, HR and payroll, dashboards, notifications, AI use cases; end-to-end UAT, final restore test, training, handover.
₹95,000
Phase prices allocate the Option 2 total. Payments follow the four milestones on the next slide. Week ranges depend on the 8-week or 12-week pace and are estimates.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
11
Notes: Source: proposal section 6 and document 2 section 2. The weeks shown are the earliest start to the latest end across the 8-week and 12-week paces. The bar is each phase's share of 4,80,000.

## Slide 12
How you pay: 30, 30, 30, 10
Each invoice is tied to a milestone and payable within 7 days. Same structure for every option.
30%
30%
30%
10%
MILESTONE 1
Kickoff
Signed order, product owner named, requirements signed off
Option 1 ₹97,500
Option 2 / 3 ₹1,44,000
MILESTONE 2
Core workflow
Commercial core and first working release demonstrated
Option 1 ₹97,500
Option 2 / 3 ₹1,44,000
MILESTONE 3
UAT build
Integrated testing and UAT build delivered to DSEW
Option 1 ₹97,500
Option 2 / 3 ₹1,44,000
MILESTONE 4
Go-live and handover
UAT signed off, go-live gates passed, handover signed
Option 1 ₹32,500
Option 2 / 3 ₹48,000
Amounts are ex GST; GST at the rate then applicable is added to each invoice. After each milestone you have 5 business days to report material deviations. No report in the window means accepted.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
12
Notes: Source: proposal section 8. Option 1 total 3,25,000; Option 2 and 3 total 4,80,000. Milestone 4 (10%) is held until go-live gates pass and the handover is signed.

## Slide 13
The first 12 months: one bundled fee
Replaces a separate warranty, testing-support charge and maintenance contract.
₹8,500
per month, ex GST, for 12 months
(₹10,030 incl. GST)
Starts at go-live, not at kickoff. Billed monthly in advance, payable within 7 days.
₹1,02,000 ex GST for the year
Defect warranty
Any reproducible defect against the signed requirements is corrected, in UAT or at any time in the 12 months.
Testing and UAT help
We help you run the agreed scripts on real jobs, reproduce and triage every issue, and review feedback with you.
Routine maintenance
Tested releases, stability and security updates, backup and restore help, administrator guidance.
Quoted separately, approved in writing first
New features, workflow changes, extra integrations, new users or sites, data cleansing, hardware faults, on-site work. Up to 8 hours a month of testing help and maintenance is included. Support after 12 months is a renewal agreed in writing.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
13
Notes: Source: proposal section 7. Support is remote, Monday to Saturday, 10:00 to 18:00 IST. We acknowledge a report within 1 business day; a reproducible defect gets a fix or workaround plan within 3 business days. Escalation: Shubhankar Rakshit, CFO.

## Slide 14
Independence, in writing
You told us a previous vendor left you without source code. This is how we address it.
Source code on full payment
The source of the DSEW-specific deliverables, in a repository you control, with deployment instructions and the database schema.
Your data is yours
Export any time: records as CSV and files in their original form with an index. No lock-in on your own information.
A perpetual licence to the platform
On full payment, a perpetual licence to the pre-existing Verity components used inside your solution. No annual or per-user fee.
What stays with us
Verity's core, reusable libraries and frameworks. This is what lets us serve other clients and keep improving your system.
The ownership and licence wording is being reviewed by counsel and is open for your own legal review before signature (document 3).
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
14
Notes: This is the largest contract risk, so say it plainly. The proposal promises source code of DSEW-specific deliverables plus a perpetual licence to pre-existing components; it does not promise the whole Verity platform source. Do not overstate. Invite their lawyer to review document 3.

## Slide 15
On your server, behind your firewall
Confidential client data stays on your own machine.
Your Windows Server 2019 host (Hyper-V)
Ubuntu Server VM · 4 vCPU, 16 GB RAM, 500 GB
Verity app
PostgreSQL
Sign-in (Keycloak)
File storage
Office PCs
Shop-floor Android phones
Backup target and UPS
Over your LAN with HTTPS. Remote only through your VPN.
Go-live gates
Production use is blocked until all six pass. None is completed yet.
Server survey done, host confirmed suitable
Install and HTTPS work, including a real-phone upload
Combined backup and restore passes on a clean machine
Sign-in and storage outage behaviour tested
UAT scripts pass
Data export reconciles with the system
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
15
Notes: Source: document 2 sections 5 to 7. We do not run Verity natively on Windows Server 2019 and do not recommend Docker Desktop or WSL there. The plan is a Linux VM under Hyper-V or a small separate host. This has not been tested on his server; a non-intrusive compatibility check comes first. His own costs: backup target and UPS about 0.8 to 1.2 lakh; a new server only if the existing one cannot run the VM, about 3.5 to 4.5 lakh (planning estimates).

## Slide 16
What we need from you, and what happens next
From DSEW
A named product owner, about 3 to 4 hours a week
Your document numbering scheme, and who owns it
Who drafts, reviews, approves and releases drawings, BOMs and test records
Samples: drawing, BOM, quotation, traveller, test report, packing list, challan
Tests per product family and the acceptance limits
Server details: make, OS, CPU, RAM, free space, Hyper-V, backup target, IT contact
Your answers on the five decisions
Next steps
1
Today
Choose an option; we answer open questions
2
This week
Mutual NDA, then your samples and server answers
3
Order
Counsel reviews document 3; you sign the order and name the product owner
4
First days
Non-intrusive server check, then a signed specification
5
Kickoff
First install on your VM; the 8 to 12 weeks begin
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
16
Notes: Kickoff is the latest of: signed order, product owner named, requirements inputs delivered. The first 5 business days after each milestone is DSEW's review window.

## Slide 17
verity
Build it once.
Customise it from your side.
So the next hundred products never need another visit to us.
PlotArmour · team@plotarmour.in · +91 87440 69597
31/44 St 3, Block 17, Vishwas Nagar, Delhi 110032
Notes: Close by asking for an option choice and a date for the five decisions.

## Slide 18
Appendix: price summary
Rupees. GST at 18% is illustrative; IGST expected, confirmed at invoicing.
 | Option 1: MVP | Option 2: Complete | Option 3: Phased
One-time fee, ex GST | 3,25,000 | 4,80,000 | 4,80,000
GST at 18% | 58,500 | 86,400 | 86,400
Total including GST | 3,83,500 | 5,66,400 | 5,66,400
12-month bundled fee, ex GST | 1,02,000 | 1,02,000 | 1,02,000
First 12 months, ex GST | 4,27,000 | 5,82,000 | 5,82,000
First 12 months, including GST | 5,03,860 | 6,86,760 | 6,86,760
Estimated delivery from kickoff | 6 to 8 weeks | 8 to 12 weeks | 8 to 12 weeks
Not included: DSEW's own infrastructure (backup target and UPS about ₹0.8 to 1.2 lakh; a new server only if needed, ₹3.5 to 4.5 lakh), external AI service charges, GPU hardware, support after month 12. Prices are fixed and not discounted further. Valid for 60 days from 20 October 2026.
PlotArmour · Verity for D & S Electric Works · Proposal meeting, 21 October 2026
18
Notes: Source: Verity_DSEW_Detailed_Pricing.xlsx, Summary sheet, and proposal sections 1, 7 and document 2 section 11. First 12 months including GST = ex-GST total x 1.18.